## Sheet1
2023-08-02
Activity | % | Submission Date | Task | Notes
Proposal | 15 | 2023-07-21
Base data downloading
|  |  | data cleaning and features identification | will try binary classification but main focus will be multiclass
|  |  | Try ML algorithms, hyperparameter tuning | DT, LR, KNN, RF-Ensemble, AdaBoost, Gboosting, SVM
Identify the best model for comparision for later use with Own created data
|  |  | Start creating own data | Use key sniffer app
Milestone Report | 25 | 2023-08-10
Complete data creation
data cleaning and features identification
|  |  | Try ML algorithms, hyperparameter tuning | DT, LR, KNN, RF-Ensemble, AdaBoost, Gboosting, SVM, Stacking/Voting
Create PPT
|  |  | Deployment (?) | Use key sniffer app, read data from csv to notebook or GUI
Create Report
Update Github (?)
Presentation | 30 | 2023-08-23 | Presentation
Final Report | 30 | 2023-08-23 | Submit Report